PROJECT MANAGEMENT DEPARTMENT

MANUAL

2017-18

(Version 1)

For private circulation only

To be circulated strictly with the permission of Management committee

CONTENTS

POLICIES

1. Mission/Strategic Plan

Project Selection Criteria

Target Level of Development Activity

Narrowing or Eliminating Production Activity

2. Governance Policies

Board Members

Articles of Incorporation and Bylaw Provisions

Entering into Contracts

Approving Deals

3. Working Capital, Cash Flow Management, and Fees

Feasibility Advances by the Consultant

Predevelopment Advances from the Consultant

Predevelopment Borrowing

4. Interdepartmental Review and Approval

Plans and Specifications

Operating Budgets

Predevelopment and Development Budgets

ORGANIZING THE PROJECT - PROCEDURES

I. Feasibility Analysis

1. Market – Market Study

2. Finance – Estimate Project Costs

3. Physical Building – Site

4. Stakeholder/Political – Support for Project

5. Project Management – Project Team

6. Board and Internal – Feasibility within Organization

II. Project Assembly and Deal Making

1. Market – Clients/Customers/Marketing Materials/Lease-up

2. Finance – Applications

3. Physical Building – Architect/General Contractor/Construction Bidding

4. Stakeholder/Political – Regulatory

5. Project Management – Consultants/Partnerships

6. Board and Internal – Recognition/Approvals

III. Construction

1. Market – Marketing Office

2. Finance – Draws

3. Physical Building – Construction Schedule

4. Stakeholder/Political – Events/Support

5. Project Management – Consultants/Services

6. Board and Internal – Response/Reports

POLICIES

1. MISSION/STRATEGIC PLAN

Project Selection Criteria

Target Level of Development Activity

Narrowing or Eliminating Production Activity

The mission of the organization (CSC) establishes the focus of the organization and identifies a need or series of needs in the students community to which the organization will respond. The Board of Directors, all of whom must believe in the mission, will be responsible for developing a Strategic Plan with the staff to set the course on how the mission will be accomplished over a specific period of time (1year, 3 year, 5 year etc). Out of this discourse and over time the Board will develop policies to guide the organization. The policies may answer:

Who are we going to serve?

Where or what geographic area?

How are we going to do it? – By housing, business development, and/or service 	programs?

The mission of an organization—which may include producing affordable student housing as a long term objective-- provides the context for the organization’s development activities.

Policy: Project Selection Criteria

Develop a policy around our selection criteria. Projects are selected based on mission, capacity, and political will. An organization must have the capability to deliver a project that is economically feasible and financially viable within a community setting where there is support from its stakeholders. The most basic questions to be asked are:

- does this project fit our mission and strategic plan?

- do we have an experienced team to manage this project?

- is there funding available for the development of this project and is the project 	 	  designed for long term economic viability?

-is there support from the stakeholders: the organization’s Board of Directors, the 	 neighbourhood, the funding community, our clients, and representatives in city 		government?

When these four major criteria come together they form a core that supports a project. That support is summarized in the figure on the next page.

Four Keys to a Project

Policy: Target Level of Development Activity – do as much as we can do with our limited resources

Develop policies based on our capacity and our resources. Development activity depends on the availability of resources. The capacity of the organization will determine the size of projects that it will develop, and available sites will determine where development will occur, but the limiting agent for all production is the availability of capital.

Multiple financial products and partners will need to be assembled for larger projects to succeed.

The key components for targeting activity are:

Availability of capital			Subsidy for rental

Capacity of the organization 		Political and neighbourhood will

Site availability 			Market forces

Develop policies regarding where we will respond to needs. In addition to the capital we must raise and our organization’s capacity, the other key considerations for development will be a combination of determining where to locate a needed housing program and a neighbourhood’s or community’s will to support or allow development of the program nearby. Assessing the market forces at work in a specific location will be necessary in making a final decision on where we will locate our project. In the end, the location and type of needed housing in our community and the neighbourhood support will all be factors in determining our housing policy.

Policy: Narrowing or Eliminating Production Activity – determine in what areas we are not going to be involved

Develop policies that will limit what we will produce. Just as important as determining our target selection criteria and the level of our development activity, is having the Board decide the areas in which we will not get involved. The mission may fit, the resources may be there, the neighbourhood would support it, but these production activities we will not do.

2. GOVERNANCE POLICIES

Board Members

Articles of Incorporation and Bylaw Provisions

Entering into Contracts

Approving Deals

The governance policies of the organization (CSC) may legally limit or set boundaries where the organization may work and may define their client/customer base. These policies may establish who has authority to bind the organization, and how decisions are carried out. The organization should monitor its own actions to be sure they conform to the governance documents.

Policy: Board Members

Board members should be people who support the organization and its mission. It is critical to have members who represent diversity and members who work in different business sectors who are willing to ask questions, provide assistance and knowledge in all aspects of carrying out the mission: real estate agents, attorneys, human service providers, community residents, accountants and business managers. The Board should establish a policy on the recruitment of new board members, always seeking out those who are willing to share their skills and dedication.

Articles of Incorporation and Bylaw Provisions

The Articles of Incorporation limit the organization’s work within its mission, and the Bylaws provide authority for those responsible for oversight of the organization’s work. From time to time organizations that have served a specific community for many years find that the boundaries have become restrictive and the organization opts to amend their documents in order to work outside of their designated area. Strategic planning will guide the organization on whether or not the documents should be amended to conform to an organization’s expanding mission. Documents can only be amended by a vote of the membership at a meeting designated for that purpose, or by the Board if given that authority.

Policy: Entering Into Contracts

The organization should annually adopt, by resolution, provisions on who may sign documents and bind the organization contractually, if the Bylaws do not specify an individual.

The Board of Directors of the organization should approve by resolution, contracts and other legal instruments and especially loans that guarantee performance by the organization and where the organization provides security in the signing of the contract or other legal document. The organization may set a policy that contracts over a specific amount must be approved.

Approving Deals

An organizational chart will provide structure on how deals are approved. The Board of Directors has final approval; however, a series of approvals may be given at various steps in the process, by various entities in the organization. Final approvals by the Board of Directors are done by resolution. See Approval Steps as below mentioned.

APPROVAL STEPS

By Entities in organization

3. WORKING CAPITAL, CASH FLOW MANAGEMENT, AND FEES

Feasibility Advances by our organization

Predevelopment Advances from our organization

Predevelopment Borrowing

The complexity of a project will drive the need for working capital during the life of a project. Cash flow management is the key to a successful project – ensuring that funding comes into the project as planned so that disbursements can be made in a timely manner to contractors and suppliers. The organization’s policies on using their own capital versus utilizing “funding capital” from outside sources should be discussed prior to the development of any project, and policies should be formulated to guide development practices.

Policy: Fees

Develop a policy for setting fees. The fee structure should be adapted to the circumstances and adjusted to enable the organization to remain viable. Risk is to be considered – make sure the developer fee we will receive is sufficient in terms of the risk involved – the larger the project, the more complex, the longer the time to develop, the greater the risk, and consequently, the greater the fee. Because development projects fees are paid at the end of the project we must figure out how to pay all organizational operating expenses until a project is completed -- which may be months, and sometimes years before those fees are available to support the organization.

Fee structures are going to fluctuate according to where we do development work as they will be influenced by the real estate market in our region and by our local government and what they will approve.

Policy: Feasibility Advances by our Organization:

Develop a policy that will support using staff time to research the feasibility of new projects. Such a policy may be unwritten but understood by all. When we or our organization are asked to look at a project to decide if we want to become  involved in the development of the project, or if the project is realistic, we must consider several things:

- Is this an opportunity that would benefit our organization?

- Is this a stakeholder, customer, or previous contact we should respond to?

- Is there a staff person who has time to do research and how long will it take?

- What do we want to know from the research?

Looking into the feasibility of a proposed concept or idea must have some value to us because we will be donating valuable staff time to do some research. The person who supervises our staff should be able to make this decision and then report to the Executive Director if we have a strong lead on a new project.

Flow chart for release of payment to vendors/ contractors:

Divide entire Project & payment into no. of sub parts

Make advance payment upon submission of guarantee forms by vendor.

Second round of payment should be done after completion of first part of project

Remaining payments should be done after completion of preceding part

Keep a part of payment for issues/renovation work after completion of project.

Policy: Predevelopment Advances from our Organization:

Develop a policy to guide us in the advancement of our own operating Rupees for the predevelopment of a project. In most instances, non-profit development organizations will not have the ability to advance (spend) operating dollars for predevelopment expenses. Only funds which have been specifically raised for project development should be spent on predevelopment ventures, and, if we have the cash reserves to do this, we can loan our project these funds at a reasonable or below par rate after developing a loan policy that meets the approval of local government agencies. In no instance should funds dedicated to other organization programs be diverted to cover project development.

Our staff’s initial project research must show the concept to be considered reasonably feasible before dedicating additional staff time and laying out cash in the development of the project. Most organizations will support the use of staff time but will borrow funds for all other predevelopment activity.

Policy: Predevelopment Borrowing

Develop a policy around borrowing that includes, (1) who determines when a loan is necessary and (2) who has authority to commit the organization, and (3) addresses the necessity of adopting individual resolutions each time we approve the financing for a new project and (4) at what stage in the process that approval should occur.

Many project expenses must be paid prior to final project approval being given. For example, our organization may hire a research firm to conduct a market study to determine the market potential of a proposed project. This study is a justifiable expense of the project and an appropriate means of determining if the project should move forward. Other examples of predevelopment expenses are environmental studies, architect drawings and construction specifications, real estate appraisals, or options on land (with the appropriate contingencies to get out of the deal if financing cannot be found).

When we look at borrowing, consider the overall cash flow needs of our project for both the pre-development and construction phases -- this will help us understand where the gaps in our financing are and how much we need to borrow. Look at the terms and conditions of loans to make sure that our organization can accept them and our project can support them. Non-profit developers must weigh the risk of taking out loans during the predevelopment phase -- if the project fails to materialize the organization will be obligated to repay the debt.

There are several well known entities that provide predevelopment loans at low interest rates for financially viable projects during the predevelopment stage. These loans are later repaid at the construction/finance closing and the cost of these loans is charged to the project.

Policy: Construction loans

Develop a policy for construction loans similar to the predevelopment loan policy but include what types of security our organization can use to guarantee construction loans. Many projects will require construction loans (sometimes called bridge loans) which begin when construction begins and continue until completion of the project when these loans are repaid or replaced by long term debt. The interest due during the carrying time and all associated closing fees will become part of project costs.

The organization should ask the following questions when borrowing:

- How much to borrow (limits)?

- What rate can the project support?

- From whom are they secure in borrowing?

- What guarantees is the Board of Directors willing to make?

- Who in the organization can contractually bind the organization?

Most non-profit developers will not have their own capital to lend to a project in order to build the project; moreover, they understand that it is better to “use other people’s money”. The prospective lender(s) will require full financial data on the organization and a pro forma for the project which will need to be updated as the lender reviews an application for financing. Once approved, the organization’s financial statements must account for any loans it incurs. It is important to time the interest payments on the construction loan, taking into account whether or not the interest is paid starting when the loan is closed, when the first draw occurs on the loan, or, when the loan is re-paid.

Note: It is also important to determine if the construction loan can be (or should be) rolled over and be replaced by long term debt from the construction lender.

4. INTERDEPARTMENTAL REVIEW AND APPROVAL

Plans and Specifications

Operating Budgets

Predevelopment and Development Budgets

Organizations that have the opportunity to have internal review of project plans and specifications, operating budgets, predevelopment and development budgets may establish a formal or informal policy to take advantage of the input by internal departments within their organization. This review should be early in the process to take advantage of their expertise. Especially valuable is input from:

Property Management and/or Asset Management

Human Service Programs

Chief Financial Officer and the Accounting Department

Call all departments together so that everyone hears the information at the same time, presented in the same way. Provide information on financing commitments, compliance or legal regulations, construction start and completion dates, and the plans and specifications, operating budgets, etc mentioned above. Keep all parties informed during the various stages of the project and hold meetings as necessary.

Plans and Specifications

Plans and specifications go through scrutiny by the Project Manager and the General Contractor with the Architect. Review by Property Managers or Maintenance Staff for operating feasibility and property management issues is advised. During the project assembly stage the plans and specifications are submitted to the City’s Planning/Zoning and Building Permit Departments. Final project approval is recommended by the Board’s Housing and Development Committee who send their request to the Board of Directors.

It is helpful to have a set of building material “design standards” established by our organization that conform to what quality we expect in each of our buildings, especially if we service our own buildings as the property management agency. Such conformity helps the Maintenance Department plan a uniform inventory – helping them anticipate what they will need to keep on hand for maintenance repairs.

Operating Budgets

Operating budgets are to be reviewed by the Development Committee of the Board, by the Property Management Division (if any) for their operating numbers, and the Accounting Department/Chief Finance Officer, for long term feasibility. Cooperation between the Project Management Dept. (PMT) and the Development Division is of particular importance because of PMT’s need to hire new staff and rent up a new facility. If human services are to be provided by the organization or a partner, their operating budgets should be reviewed by the developer and funding requests should be discussed. Timetables for the turnover of services must be determined and departments must be kept informed concerning progress. Final budget approvals are an integral part of project approvals which are recommended by the Housing and Development Committee and then sent to the Board of Directors.

Predevelopment and Development Budgets

Predevelopment and development budgets are reviewed at various stages during the development process. Predevelopment budgets are reviewed by the Project Manager, the Housing and the Development Committee of the Board, and the Board of Directors. The same is true of the final development budget. The organization’s Chief Financial Officer/Accounting Department and/or Asset Manager will be asked to review the budgets for advice and input concerning debt obligations.

A typical project may begin this way:

A development Manager follows a promising lead and brings it to the attention of the Housing and Development Committee of the Board of Directors. The Development Committee asks for more information and the Manager continues to follow the lead, completes a feasibility study, talks with all internal departments, and brings it back to the Committee with additional information and a predevelopment budget for approval. The Committee in turn takes it to the Board of Directors where a review of the opportunity is considered and where approval is given (or not given) to proceed within specific perimeters (concept approval). When the Board gives concept approval a development team comes together to work on various aspects of the project including financing, hiring the Architect and the General Contractor. The project is assembled and brought back to the Board for approval of all the financing packages and final project approval. This occurs just prior to closing on the financing at which time the contracts are signed and the project is fully funded and those funds are “banked with the Title Company”. Construction and marketing begin and the Project Manager monitors the project until it is completed and sold or leased at which time the final closing occurs and all remaining funds are disbursed.

Review Summary: All of these rounds of review and approval result in projects that may look quite different from the original concept. Having a policy that includes project review with all stakeholders will provide us with valuable insight as well as continued project support.

ORGANIZING THE PROJECT – PROCEDURES

Project Flow Chart

Every project has 6 components: Marketing, Finance, Physical Building, Stakeholders/Political, Project Management, and Internal/Board. These 6 components of the project can be organized chronologically into 3 stages: Feasibility, Project Assembly, and Construction.

Six components:

Market

Finance

Physical Building

Stakeholder/Political

Project Management

Board and Internal

ORGANIZING THE PROJECT – PROCEDURES

- FEASIBILITY ANALYSIS

1. Market – Market Study

2. Finance – Estimate Project Costs

3. Physical Building – Site

4. Stakeholder/Political – Support for Project

5. Project Management – Project Team

6. Board and Internal – Feasibility within Organization

Assessing the Feasibility of the Project

The first stage is assessing the feasibility of the project, which is done by various entities in the organization, by the stakeholders and with the help of consultants. The end result is an affirmation of the project moving ahead, or the project being rejected, or the project being redesigned so that it meets approval. This section is devoted to assessment.

A flow chart, ASSESSING PROJECT FEASIBILITY is available on the next page.

I. Feasibility Analysis

1. Marketing

Market Assessment – For Sale

Market studies are typically done during the feasibility stage of a project -- by hired consultants to provide the research on which we will determine whether or not we should go ahead with the project. The market study should help us determine the economic feasibility of the success of our project by analyzing:

- The customer base in the market area,

- The competition and the need for additional housing products,

- The range of options and pricing available to the customer and whether or not our

Pricing is consistent within the area for the unit size we will develop,

- If there are enough customers to buy our housing product at the price we wish to 	   set;

- Various demographics in the community including whether or not our customer 	   base resides in the community, transportation, jobs, and shopping available.

Market Assessment – For Rent

Market studies for rental housing look at the demographics of the targeted housing population that will be served in order to provide information on where a project might successfully be built and where there is a critical need.

2. Finance

Feasibility/Financing

Estimating project cost is done early in the process -- using current square footage building costs, land values, basic marketing costs, consultant fee costs and costs to borrow, insurance and legal costs, and by computing a developer fee. Rental income and operating costs can be obtained from Property Management Company. Plan for how we will fill the gaps in funding with various scenarios. Take our plan to the Business Development Dept. for approval and then with their recommendation, to the Board of Directors for approval.

Filling the Gaps – Amortized Debt and Subsidies

Critical to our project is our assessment of the gaps in our financing. There are a number of ways to look at this:

For-Sale Housing: How will we subsidize the cost to build the units we plan to sell so that they are affordable to our target market? Are there private sources of funding in our community that support affordable housing initiatives? Are there city, or state initiatives that provide funding for student housing? On the central level, will our project fit their requirements? Can we turn to other established national organizations that support student housing? The application process can be lengthy and may require the assistance of consultants. Begin inquiries early in the development process.

Rental Housing: How much amortized debt can our project afford? In order to determine this we must develop projections for the operation of the project over a lengthy period of time, 10 years should provide a sufficient sample. Consult a Property Management Company for assistance in developing a pro forma that accurately represents daily operations: assesses rents and rent increases, loss of rents through vacancies and turnovers, marketing and management costs, on-going maintenance and finally maintenance reserves. Understand where the cash flow problems will be and how we plan to address them in our development and operating budgets.

Financing Programs: Have we looked into an option for us? Can our project afford the cost of receiving Government financing? If we are not familiar with the various funding programs seek out advice from other non-profits or a consultant.

3. Physical Building – Site

Site selection Assessment

Site selection will be critical to our project. We may be working with a partner that has a site selected which then we must analyze to see if it will fit our needs. We may need to work with a real estate agent to locate a site to fit our project. Some of the criteria for selection are:

- Size of the parcel (will it work for our project?)

- Cost of the parcel (can we afford it?)

- Does the site fit our needs and our location?

- Will it be available when our project commences?

- Will we need to clear the land, if so will we be relocating current tenants?

- If relocating current tenants, do we have a good understanding of relocation

requirements and the cost to our project?

- Will stakeholders approve of the site (will the neighbourhood support it, will the 	   local government approve, will our Board approve)?

- Is there a history of soil or other environmental problems that need to be resolved?

A flow chart, FINDING A SITE, is available on the next page.

Schematic Site Plan

Early in the feasibility process it will be helpful to develop various options to review with our stakeholders. Holding a design charette to involve the community so that the neighbourhood, the local government authority, supporters and or partners can come together to work on a concept plan, will give all our stakeholders the opportunity to be involved in providing feedback on what should be built on a site and how our development project will look.

Design Charette

A Charette is a workshop in which a facilitator works with the participants – usually the stakeholders (public/private supporters, neighbourhood representatives, developer, architect, service agencies etc) to develop a project concept. Often the facilitator is the lead architect for the project or someone with the expertise of a designer. The project concept can include a site rendering, a building concept, and amenities associated with the proposed site.

4. Stakeholders/Political

Support for our Project

It is easier to do a project when we have the support of all our stakeholders. Understanding the political base - what the neighbourhood wants, and what the local government and funding community will support - will help we win support if our project fits their needs. However, sometimes projects move forward without the key support of some community members or other special interests. To do so there must be strong political will to ensure funding, and unwavering support from the Board to provide moral support for the development team to move forward.

Letters of support from stakeholders are necessary in the application process for a variety of central, state and local funds. These letters provide recognition for and show the level of support for the project.

Communications and Reporting - Neighbourhood Approval

Meeting with and personally reporting to the neighbouring community or organized neighbourhood association is important for cooperation. Our understanding of what the neighbourhood strategic plan includes will help we develop with the neighbourhood a product that meets their strategic plan goals. If a neighbourhood representative is not part of the development team, keeping the neighbourhood “in the loop” can be done by:

- Incorporating representation from the neighbourhood at meetings during pre-	development discussion;

- Meeting monthly to answer questions and concerns of the neighbourhood and 	keeping the neighbourhood informed during the build-out of the project;

- Including neighbourhood representatives in the planning for public events for the 	project.

The neighbourhood’s support is vital to a project and in some instances the lack of their support has been the road block disrupting projects and causing them to be under-funded or rejected by their local city council representatives.

5. Project Management

Determining the Team

Complex projects will require putting a team together in the feasibility stage to provide expertise and input. As the project progresses consultants will be added as needed.

Each development project will have a team. The basic team is the project manager, the architect, the general contractor, and the title company. The way our organization hires the major components of the team will depend on the source of our funding and whether or not we are required to publicly bid out contracts for our project.

To confirm our hiring policy we may be asked to provide a Certificate of Compliance from our local municipality for receipt of our organization’s current Affirmative Action Policy. In addition to local affirmative action hiring policies and goals, our organization’s mission may establish higher organizational minority hiring goals for our project that encourage minority businesses and trades-people to bid on our projects. We should discuss our goals during the feasibility phase of our project to ensure compliance by contractors and suppliers and to incorporate our goals in our bid package(s).

Identify Needs

The scope of our project will set the parameters for identifying the resources that we will need to organize to have a viable project. In addition to the basic team we may need to add a marketing consultant and a real estate broker to the team. The complexity of our project may require that any or all of following be hired by the developer to provide expertise and resources:

Appraiser

Insurance Broker

Attorney

Auditor

Relocation Expert

Property Management Company

Environmental Specialist

Real Estate Broker (for site assembly or marketing for-sale units)

Description of Organization Chart Participants:

Board of Directors – This Board is established by the Articles of Incorporation and the Bylaws to be responsible for the actions of the organization. The Board approves policies of the organization and commits organization funds, and approves debt obligations of the organization.

Housing and Development Committee of the Board – On authority of the Board of Directors, this volunteer committee is formed to review and recommend to the Board projects to be developed by the organization, and to follow the progress of projects that have been approved. The Committee recommends housing policy to the Board.

Executive Director – The Executive Director (CEO) leads the organization and manages the day to day operations of the organization.

Administration –The administration includes staff assembled to lead various departments of the organization and manage the day-to-day operations of the organization.

The Development Department (or Division) of the organization oversees the progress of the project. The development staff involved in the project report to their supervisor, usually a department head (Director of Development) in the administration.

Internal Project Team – the team organized internally at the CSC may include those in accounting, legal, property management, asset management, housing services, and public relations and communications.

Project Manager - The Project Manager coordinates all aspects of the project with the Project Team and reports to the Director of Development -- the Director of Development reports to the Housing and Development Committee of the Board.

↑

Project Coordinator – The Project Manager may work with a Project Coordinator who reports to the Project Manager and is given direction by the Project Manager

Marketing Coordinator (Consultant) -- The project may require the experience of a marketing consultant to develop and coordinate a marketing plan for the project. The consultant is a project cost and paid out of project funds.

General Contractor (GC) – The GC is hired by the organization to build the project according to the plans and specifications and timetable on which the GC bid and for which the GC was awarded the construction contract. The GC may be required to post a bond guaranteeing the construction of the project; the GC will be required to furnish a certificate of insurance for his company and for all the subcontractors with whom the GC will be working. The GC works with the Architect and reports to the Project Manager.

Construction Supervisor – The construction Supervisor works for the GC and, at the direction of the GC, may also report to the Project Manager, but is responsible to the GC.

The Construction

Description of Organization Chart Participants (cont):

(Construction Supervisor, cont)

Supervisor supervises the daily operations at the construction site and makes recommendations to solve problems. The Construction Supervisor works with the Project Manager and the Architect to resolve differences as they develop including change orders, draw requests, and other concerns, to the Developer’s (Owner’s) satisfaction.

Architect – The Architect is one of the first to be hired – often to lead concept workshops, but primarily to design the project according to the criteria set forth by the Developer and within the restraints of the Developer’s budget. The Architect is responsible for value engineering and may assist the Developer in putting together an efficient team to build out the project. The Architect signs off on the draws and may be hired at an additional expense to inspect the project and confirm that the project is being built to specification.

Legal/Title Company – A Title Company is selected by the Developer to close the financing on the project, provide Title Insurance for the project, review the draws and disburse payments for the project, receive all lien waivers on the project, and perform the final closing and reconciliation for the disbursement of all funds for the project. The Title Company works with the Project Manager on any discrepancies or problems that need resolution and may establish an escrow to hold funds for final distribution.

A major piece of the project is the legal component. The legal documents of the project will be drawn up or reviewed by outside counsel who may or may not work on a pro-bono or reduced fee arrangement with the CSC. Because the legal work is critical to the success of the project, it is imperative that consul knowledgeable in real estate transactions represent the organization.

6. Board and Internal

Feasibility within the Organization

Test the feasibility of the project within our own organization. If we do our own property management, review the operating numbers with them to see if our projections are realistic. The accounting department and those doing asset management may need to review our pro forma. When our predevelopment budget has been reviewed meet with our Housing and Development Committee to go over our concept and our numbers. Ask them for preliminary approval.

APPROVAL STEPS:

1st round of approvals: Concept Resolution (they like the idea)

↓

2nd round of approvals: Financial (they closely review the financing and timing of the deal)

↓

3rd round of approvals: Final Approval Resolution (they approve the contracts that close the deal)

BY ENTITIES IN ORGANIZATION:

Board of Directors

↑

Housing and Development Committee of the Board

↑

Development Project Manager with Development Director

II. PROJECT ASSEMBLY AND DEAL MAKING

1. Market – Clients/Customers/Marketing Materials/Sales or Lease-up

2. Finance – Applications

3. Physical Building – Architect/General Contractor/Construction Bidding

4. Stakeholder/Political – Regulatory

5. Project Management – Consultants/Partnerships

6. Board and Internal – Recognition/Approvals

1. Market

Clients and Customers

Following concept approval and prior to construction, it will be helpful to redefine who our customer is, is there sufficient demand, and exactly how we will reach them. A marketing strategy will organize our approach and provide us with a timetable for reaching our customer. Work with our marketing team to network with colleges/universities and referral agencies -- to inform them about our product/services and when it will be available. Periodically we will need to assess our progress, our pricing and our approach to guarantee our success. Our marketing team may include consultants, real estate broker or sales agent, public relations and communication advisors, and event planners.

Marketing Materials

Depending on the scope of our project, the marketing materials we need should be developed to advertise our product. We may want to “name” our project for visibility and identification, develop a logo and brochures with product information – unit size, amenities, location and services. We may want to work with the public relations and communication staff in our organization to coordinate a series of events around our project (ground breaking, opening of a marketing office, news about the first renter/student etc). Information about these events becomes part of our marketing strategy.

For-Sale

On a parallel track with the development of our project, will be the marketing of the project. We may be required by financing agreements to pre-sell a percentage of the project before construction can begin. This means that marketing can begin in earnest after we have received approval of project financing.

The Developer should review with the marketing agent all details regarding income requirements and any other criteria imposed by project financing.

Reservations for for-sale projects may be taken up until purchase agreements can be legally offered. If disclosure materials are required as part of the sale, they should be provided according to the limitations required by law. There may be other pre-sale requirements imposed by our state; our marketing agent and hired broker-agents must be familiar with these regulations. Post the equal housing opportunity logo with and/or on our marketing materials

Rental – Rental applications can be accepted by our Property Management Agent after financing has been secured. The Leasing Agent should request a rent matrix from the Project Manager showing every regulatory condition and to which apartments they apply. Confirm the construction completion date of the housing units and ask how “solid” it is. All of our marketing materials should display the equal housing opportunity logo.

2. Finance-Applications/Proforma

Funding Application Preparation/Tipping Point

Critical to our project timeline will be the timing of funding applications. Careful study of  funding rounds occur, their application due dates and selection dates, will direct the schedule for much of our activity during the project assembly stage. Most projects today require multiple funding sources; workshops may be available to assist developers as they work through the maze of funding requirements and deadlines as they develop their pro forma.

If we are planning to use Tax Increment Financing (TIF) our funding application (and approval) will need to be adjusted to the calendar year. If we do not begin construction in the calendar year in which our credits are approved we will be required to file to carry over our credits into the following year which might significantly impact the cost of our project.

After filing finance applications the project will continue to move forward in the project assembly or development stage while we await news of approvals. If keen competition, lack of support from a major stakeholder, or other reasons lead to a denial of our funding request(s), our project will be in jeopardy. This is the “tipping point” -- where we must decide if we re-group and try again, or thrown in “the cards”. A frank discussion with our stakeholders and Board, with a realistic look at our options and the impact of delay to our project, will determine if we go forward or abandon the project.

Construction and Permanent Financing

Construction financing provides gap financing during the time the project is being built and before closing on permanent financing at the end of construction; it is often referred to as “bridge” financing. Because the bank approval process is a lengthy one, starting with a loan officer and going through a number of loan committee reviews, the process should begin as soon as concept approval has been received from our Board of Directors, and applications have been submitted for project financing to various governmental agencies and foundations.

Construction financing most likely will not be approved until other project financing is in place with application selections having been made public. Many financing requests will be contingent on other financing having been approved. Closing on construction financing occurs at the closing on the purchase of land, or of a building on the site to be re-developed. Following the development of the site and when the occupancy certificates have been authorized, the construction financing may convert at another closing to permanent financing.

With Sworn Construction Statement

Program Budgets - Working with Service Providers

When developing a project that incorporates services for residents, a program budget must be developed. At the least, this program budget should identify the sources of income for the program, the feasibility cost, start up costs, and the cost of the first year of operation. As with all budgets, the expertise of the person providing the budget numbers will determine the accuracy of the estimate. The program budget numbers may be incorporated into the funding requests in our project pro forma or we may wish to raise operating funds independently from the construction project.

3. Physical Building – Architect/General Contractor/Construction

Hiring an Architect or a Contractor

The hiring process for both the Architect and the General Contractor (GC) are similar. There are several methods that can be used for seeking a General Contractor:

1. Public advertising through a Request for Proposals (RFP), often done when public funds are assigned to a project. The responses are evaluated for total construction costs and the lowest responsible bidder is chose.

2. Public advertising through a Request for Proposals (RFP). If we are selecting only a General Contractor, the selected contractor bids out and hires the sub contractors.

3. No public advertising. A qualified contractor is selected and the developer and the contractor negotiate the bid.

Three flow charts are presented in the following pages:

THREE WAYS OF FINDING AN ARCHITECT, THREE WAYS OF FINDING A CONTRACTOR.

Design standards

The project that we are designing may have very specific requirements that must be identified – design standards – that will be incorporated into the Architect’s design of the project. The design standards might be a template of standards that our organization insists are included in every project that we construct, or they might be quite simple.

- All projects must be in the character of adjacent neighbourhood housing,

(two-story with gabled roofs and detached two car garages);

- All Projects must have front porches, and wrought iron fencing no higher than 3 	   feet in the front yards;

- All contracts must be air conditioned with all appliances furnished, and

-The contractor must incorporate standards for buyer options for electrical fixtures, 	  carpet, interior paint colours, and kitchen and bath cabinets and counter tops.

Developing the Building Plans/Bidding out the Construction Project with an RFP

When the Architect has completed the first of many drafts of the building plans and specification, the plans will begin to go through a series of reviews with the Developer and the stakeholders. After the Developer approves the final draft of the plans they are submitted to the local municipal Planning, Zoning, and Building Inspection Departments for approval. These departments may require minor (or major) changes which the Developer and the Architect will need to address. Once all the regulatory agencies have been satisfied the project can go out for construction bidding.

If required by central or local regulations, the construction project is advertised to the public using an RFP to solicit bids. The bids are received by a specific date and time on a bid form and opened at a public forum. The bids are announced and the lowest qualified bidder is awarded the contract for construction of the project. The price, conditions of the contract including change order requirements, fees for additional work, penalties or liquidated damages for missing the completion date, etc are included in the construction contract.

General Contractor/ Benefit of using negotiated bid for GC services

One of the benefits of choosing the GC by a negotiated bid is the availability of the GC early in the project assembly process to provide a preliminary construction cost analysis for budget purposes. Having this information early gives the Developer more latitude to request changes in the design of the project to fit the funding available if the projected construction costs are deemed to be too high.

Architect – value engineering

One of the most valuable aspects of hiring an Architect familiar with affordable housing projects is the ability of the Architect to provide value engineering to keep the cost of the project down. Value engineering is the examination of “function or performance” to reduce the cost without reducing the quality. This evaluation is done with the General Contractor and the Project Manager-- to analyze the building plans and specifications to remove unnecessary expenditures in the project costs, often by substitution of materials, sometimes by re-design.

4. Stakeholders/Political

Build Political Support

Neighbourhood approval of our project generally means political support will follow.

Keeping the neighbourhood informed and as an advocate for our project will be easier if the neighbourhood has representation as part of our original concept planning team. Ask for advice and incorporate as often as possible the feedback that we receive. The neighbourhood may be a partner in our project, or they may be our customer. Whatever their relationship, keep them informed about environmental issues, market challenges, design or construction problems by being straightforward when we report at meetings. Keeping them informed through written reports will provide them with a tracking system for reference for their constituency.

Political Objectives

Sometimes there will be a political agenda tied to a project. The objective of policy makers may be to solve an ongoing problem in the community. Understanding the political will, available financial support and neighbourhood climate will be imperative to moving a “political” project along.

Regulatory approvals - Zoning Analysis

Recognizing and acting on problems arising from concerns regarding regulatory approvals is another part of assembling the project. Especially troublesome can be zoning issues involving set backs, parking, building height, the number of units to be clustered on the site, etc. Requesting variances or working with the city Planning and Zoning Department will be necessary in order to move the project ahead. We will need to work within the timeline furnished by the municipality for public hearings and comply with documents that are requested. Each city has their own ordinances – it is up to the Developer, the General Contractor and the Architect to know these ordinances and to comply with them. Make sure our site, physical building and concept plan are acceptable to the zoning department of city.

Another zoning issue may involve service-related housing for specific cliental. Our community may have ordinances regulating how many supportive service housing projects can be operated in a neighbourhood. Zoning for these projects may require independent efforts to change minds and influence constituencies to support our project. It may be an up-hill fight and require going to court for a ruling allowing we to continue.

5. Project Management – Consultants/Partnerships

Hiring and Managing Consultants

Our project may have very special needs that our organization cannot provide - hiring experts to help we solve problems will be critical to our success. We may have to advertise by an RFP for these consultants, we may be able to negotiate directly with qualified individuals or agencies, or we may be fortunate to have others who will assist on a pro-bono basis. Work with our local government agency to determine what contracting requirements we must follow based on the underlying funding for our project.

We may need the expertise of some or all of the following consultants:

Engineers – soil engineers for environmental issues, structural engineers to provide opinions on building integrity

Legal – attorneys to draw up partnership agreements.

Financing, review closing documents,

write portions of our financing applications, provide expert advice on relocation issues

Marketing – consultants to provide a marketing plan, real estate brokers/agents to sell

or lease our housing product, graphic artists to develop a logo or a project identity.

Legal

Often a non profit organization will have an attorney at their disposal who can give pro bono advice, and some attorneys will offer to provide services to non profit developers on a reduced-fee basis. To assure our partners that we have done our due diligence and to protect our organization from lawsuits, it will be important to hire an attorney(s) who specializes in this type of real estate development to provide us with competent advice as we develop our project. The extent of the attorney’s involvement will depend on how complicated our project will be:

- Do need help analyzing loan documents that revert to grants that will subsidize the 	cost of construction?

- Will we be establishing a LLP (Limited Liability Partnership) to develop a	housing 	project using TIF financing?

-Will we need a TIF opinion?

- Are we taking on a project with the scale of a PUD (Planned Unit Development) that 	requires a large block(s) development plan for townhouse and or condominiums and 	need an attorney to negotiate the terms of our agreements and develop our 	disclosure documents?

All of these legal issues require expert consul. Our project may require that we assemble a group of attorneys, each with their own expertise in the area in which we will need assistance. If we do not know a good real estate attorney ask our fellow housing developers for their opinion to determine who the experts are in our region.

Communications and Reporting

Detailed reports are expected (and necessary) in complex projects. The internal team will keep reports of every meeting and they will generate progress reports monthly to the Housing and Development Committee and to the Board of Directors according to Board policy. We may also need to file periodic reports with syndicates (limited partners), loan officers at banks or other financial lenders, sponsors, and others with a substantial interest in our project.

EXAMPLE: Quarterly Report

FROM: Developer

WRITTEN BY: Project Manager

TO: Partners, Financial Lenders, and Sponsors

RE: Update on project timeline, current status, financial situation and current

Pro forma, critical next steps. Request for approval(s) as necessary.

Progress Reports (Internal Team and Board members)

The progress report is a tool to keep communication open during development and construction of our project. The internal team (staff working for the Developer) will keep memos and meeting notes to chart the course of the project insuring that decisions that are made are documented and followed. The weekly construction meetings will be written up by the GC and distributed to those attending for approval and corrections. These progress reports track all changes made during construction and when consensus is needed regarding problems as they develop.

Maintaining and Solidifying Partnerships

Stakeholders may be partners in our project in the legal sense, or merely interested supporters. Our communication with the stakeholders – and ensuring that they are “at the table” during the concept stage of the project and kept informed during the project assembly stage – will give them a “stake” in the outcome of our project. It will be necessary to inform them when we encounter problems that directly impact the project (political issues, environmental roadblocks, financial setbacks that may slow or halt our progress). Keeping the stakeholders “in the loop” with written correspondence as well as in verbal discussions will help them remain confident in the direction that the project is going.

File Management

Project Managers find themselves inundated with paper by the time they are well into assembling the project. The single file they used in the concept stage during predevelopment has now merged into a comprehensive filing system to help keep track of all documents.

6. Board and Internal

Financial Review and Approval

The Board of Directors and the Housing and Development Committee will be following the “deal making” and assembly of the project closely after they have given concept approval. All of the affected departments in the organization will be providing input as the project becomes a reality. The Board must also receive notice of major changes to the project as they develop, and of any variances that they must approve for the project to proceed. After the financial applications have been submitted and approved by various funding agencies, the Board will receive our request for approval to borrow funds. When the Board approves the “borrowing resolution” the project will have “go ahead” status and the development team can begin to prepare to close on the construction financing.

The Borrowing Resolution Check List: The following items appear in a borrowing resolution:

- Opening description of the ownership entity of the project;

- Name of the sponsor and/or of the developer;

- Statement about the general partner, if any;

- List of the funding sources, the amount, how secured, and a copy of the physical 	documents attached as an Exhibit;

- Authorization to be part of a limited partnership, if any, to develop the project;

- Authorization by named individuals in the company to execute documents in 	connection with the development of the project, naming the documents and the 	loan or grant amounts including the construction documents and 	contractor/consultant contracts, limited partnership documents, and development 	agreement.

- Naming specific individuals as general partners in the partnership and giving the 	individual authority to execute and deliver documents, reports, certificates etc.

- Stating that the authority given in the resolution shall continue until written notice 	of rescission or modification is made.

- Ratifying and approving actions previously taken and documents executed by named 	individuals.

Certificates:

- Separate certification stating that the undersigned is the Director of the 	Corporation and that the resolution(s) was adopted by the Board at a meeting (date 	noted) for which notice was given and a quorum was present;

- Separate certificate that the attached is a true and correct copy of the resolution 	unanimously adopted at a meeting called in compliance with laws, requirements etc.

III. CONSTRUCTION

1. Market – Marketing Office

2. Finance – Draws

3. Physical Building – Construction Schedule

4. Stakeholder/Political – Events/Support

5. Project Management – Consultants/Services

6. Board and Internal – Response/Reports

1. MARKETING – Marketing Office

Having a marketing office at the construction site is a plus in promoting our project, especially if we are developing a for-sale project. The opening of the marketing office is cause for celebration and another way to publicise our project and what we are offering. All of our sales material must be ready for the opening of our office and our sales staff should be primed with any and all marketing details. A visitors book will help keep track of people who drop by, and especially useful for making “call-backs” and keeping track of daily traffic. It will be important to post visible signs locating our office and our business hours, and that we are an equal housing opportunity project as we conduct our marketing efforts.

For-Sale: Working with the Contractor

The Developer and the General Contractor with the marketing staff should determine what, if any, options will be offered with for-sale housing. Will buyers have the opportunity to select carpeting, appliances, and fixtures? If so, deadlines for ordering and samples of options should be provided in the marketing office and any additional cost should be presented in writing with multiple copies for all parties.

Disclosure Documents: Housing projects will have multiple disclosure documents. Sometimes property owner will have covenants attached to the land which also must be disclosed. These disclosure documents which are required by law are part of the purchase agreements and are provided within specific time constraints which protect prospective buyers who many after reading the documents decide to cancel their purchase agreement. The marketing agent must provide these documents upon request and may ask for a deposit while the documents are in the possession of the prospective buyer.

SAMPLE VERIFICATION ON RECEIPT OF CONDO DOCUMENTS

For Rent: During the construction of a rental property, the lease-up and qualifying of renters is the main focus of the marketing staff. It will be important to stay in contact with tenant applicants to update them if the construction schedule and completion date change.

2. Finance - Draws

Draw requests/inspections

A draw request is a legal instrument in which the General Contractor requests payment for completion of a portion of the construction to-date. The key here is completion.

The Developer and the General Contractor (GC) must agree prior to the signing of the contract if the Developer is going to pay for materials delivered to the construction site but not installed. The Construction Contract will also state the percentage of each draw that will be withheld until the end of the project when completion, approval, and sign-off by the regulatory agency(s) have occurred. For the sake of this Policies Manual we do not recommend paying for materials that are not installed, and 10% withholding is standard.

When draws are submitted by the GC, the Architect will inspect and sign-off on the installation of materials and that portion of the construction included in the draw. When draws have been signed, copies are sent to the regulatory agency (government) overseeing the project for approval. When the regulatory agency approves the draw the original is sent to the Title Company for disbursement. It is important for the developer to be “on top” of the draws to insure that the GC receives timely payment for his work. Partial lien waivers for work completed to-date by subcontractors should accompany the draw. (Copies of the draw may also be requested by other lenders or financial partners involved in the project. Their approval of the draw request may also be required.)

Draw request from General Contractor

↓

Architect reviews and approves and signs

↓

Developer/owner reviews and approves and signs

↓

Regulatory Agency reviews and approves and signs

↓

Title Company reviews and approves and disburses funds

Change Orders

A change order is required when an item which was to be included in the project is not available and the contractor or architect wish to make a substitution, or when something unforeseen occurs and requires additional materials (and cost) to rectify. The Construction Contract will include the cost associated with responding to a change order – perhaps a 7% fee per change order will be charged to the project. The change orders are the responsibility of the GC and are to be approved prior to being attached to draw requests. They are signed off (approved) by both the Architect and the Developer/Project Manager. The Project Manager must be aware of the additional (or reduced) cost to the contract and must have available funds for increases to the contract.

3. Physical Building - Construction Schedule

Construction Schedule

Monitoring the construction and tracking the construction schedule will be a daily task of the Project Manager. The Architect may be compensated for providing inspections during the construction period but it will be the Project Manager who will work closely with the construction site Supervisor to keep the project on track. The construction contract may identify a penalty for bringing in the project late, or a bonus for bringing in the project on schedule or early.

Construction Reports

The General Contractor (GC) will hold weekly meetings at which time minutes will be taken and then transcribed by the GC for all in attendance. These minutes will become the basis for following the build-out of the project. At the Construction meeting the Project Manager and the Architect will have the opportunity to voice concerns with the GC and have those concerns put into writing. In complex projects concerns may be addressed on 3-ply forms that are filled out and copied to various parties with an interest in the project.

Punch Lists

When the GC notifies the developer that the project is completed and the final building inspections are occurring, the Developer and the Architect will inspect the building for unfinished work or work that needs repair noting the location and the action that is required. This written list is a “punch list”. The GC or the Architect may have forms in triplicate that are used for this purpose. The General Contractor will send these lists to the subcontractors who are responsible for the work. Any work that remains incomplete should be noted by the Developer and funds should be withheld from the final payment to the General Contractor -- enough to cover the cost of the work (generally not less than 150% of the cost to perform the work, and often 200% of the cost to finish the work). The funds withheld are placed in escrow with the Title Company to insure that money is available to complete the project.

Warranties

Warranties are provided on certain materials or equipment supplied and on installation of those materials. Our state may require a 2-10 warranty on general workmanship (2 year warranty for electrical and plumbing and 10 year warranty on the structural integrity of a building). The Developer should require a one (1) year warranty on all workmanship so that the owner can expect repair or replacement of defective materials or workmanship during the first year of operation.

Project management for upliftment of existing building into student housing:

Consider the number of rooms, the number of students who will stay in each room, the views from each room and whether the shared facilities, such as bathrooms and dining halls, will be enough for all students at maximum occupancy. We have to meet the building codes of local authority and may have to go through inspections and obtain building permits.

Flow chart for new construction/upliftment of building into student housing:

Structure of construction/renovating a building into student housing

Create Foundation plan, bar drawing, Slab cast drawing, column/beam drawing for Structure of building.

For interior plan the following steps should be followed

Based on Electrical drawing make conducting and filing

Create plumbing drawing

POP punning, false ceiling

Wooden frame work

Flooring (PCC/tile work)

Painting

Electrical & Plumbing fixtures

At last connect main  electrical power supply, install DG set, R.O water system, boilers, A.C system, C.C T.V’s, L.C.D, Fire extinguishers, cots, wardrobes etc.,

### Architectural Drawings

- Name and address of project

- Scaled and dimensioned floor plans with all room names labelled; doors and windows shown; and special features clearly noted

- Exterior elevations, showing all openings

- All door and window sizes noted either on elevations, plans or door and window schedules referenced to plans. Indicate sleeping room and basement egress.

- Complete sections and details for foundations, floors, walls and roofs, with components of assemblies completely noted, properly cross-referenced, with floor-to-floor heights dimensioned

- Indicate compliance with braced wall requirements, indicating the specific methods used and details of the method(s) in the construction documents. (See below for additional information)

- Indicate compliance with Energy Code. Show insulation values plus mechanical drawings as required below.

- Indicate stair dimensions, tread and riser dimensions, handrail and guardrail information.

- For additions and renovations, make clear the distinction between existing construction, alterations to existing, and new work.

- For two-family residences, duplexes and townhouses, indicate rated walls, provide a copy of the testing agency design detail(s) on the drawings, and show compliance with other required dwelling unit separation provisions.

Wall-bracing plan review & inspection requirements

- The IRC wall-bracing method must be noted on the submitted plans, with areas of braced walls shown on elevations and interior braced wall length shown on floor plans. The areas of braced wall must be clearly and obviously shown and noted, by darker shading or some other standard black and white graphic method. Connections, details and nailing schedule must be shown on plans. Details showing continuous load path and uplift resistance must be shown (i.e. wall sheathing lapped over rim joists or metal strap connections of walls to floor system, etc).

- Construction drawings must include design details of portal frame, standard manufactured shear panels or other pre-engineered approved methods, if used.

- Structural calculations bearing the dated signature and seal of a design professional registered in the Commonwealth of Virginia are acceptable as an alternative to prescriptive design.

- Before installing building wrap or windows, approved braced wall panel and nailing inspections are required.

Structural Information

- Note uniform design loads and any special loading.

- Scaled and dimensioned foundation plans. Show ventilation and access openings as required.

- Scaled and dimensioned floor and roof framing plans. Indicate all beam sizes, headers, ledgers, posts and columns. Note species and grade of lumber, or manufactured structural members performance grade.

- Sections and details properly referenced to plans

- Reinforcing steel, if used, for slabs, retaining walls, grade beams, foundations and foundation walls

- For additions and renovations, detail the existing structure and footings that provide bearing for new work.

- Structural calculations, signed and sealed by a structural design professional, licensed in the Commonwealth of Virginia, for those structural elements that exceed the tabular values set forth in the code, and for retaining walls with a difference in grade of greater than two feet.

- General notes and construction notes

Mechanical Plans

- New dwellings require:
– heating/cooling load calculations
– duct layout
– complete mechanical layout and the equipment list (type and size) including exhaust system for kitchen, baths and dryer, venting systems and combustion make up air for fuel-burning appliances prepared and signed by a licensed contractor, or architect or mechanical engineer with sealed drawings.

- For alterations or additions to existing dwellings, the same requirements apply. However, the applicant has the option of attaching the Mechanical Plan Requirement Waiver form, signed by the property owner, to all sets of drawings. This allows the required information to bypass mechanical plan review and be reviewed at a later date by the field inspector at the time of the mechanical inspection.

- When adding or replacing exterior units, a scaled, certified plat is required. It must clearly indicate the location of the new or replacement unit(s).

Plumbing

- New houses will show the water service location and pipe size on the site/grading plan.

- Renovations and additions to existing dwellings may continue to use the existing water service.

- Plumbing riser diagrams are not required, except for unusual features such as solar water heating systems.

- All projects will show plumbing fixture layouts as part of the architectural plans.

Electrical

- Compliance with the IRC for electrical is by field inspection only.

- We need to review any boxes, devices, switches, towers, conduit, etc. that will be installed within the right of way. Plans shall show the riser diagram and a profile of purposed equipment.

4. Stakeholder/Political – Events/Support

Maintaining Support throughout Project

Keeping the stakeholders informed during the build-out of the project can be done through reports and by a series of events at the project. The Project Manager can also address the stakeholders at various times during the construction phase at meetings designed to inform various constituencies as to the progress of the project.

Celebrations bring people together and provide visibility for new projects. Various milestones in the project can become times to celebrate:

- Ground-breaking and construction start;

- Raising the first wall or topping off a building;

- Completing a unit and opening it as a marketing office;

- Conducting tours when construction workers are off-site;

- Building a playground.

5. Project Management – Consultants/Services

Managing Consultant Activities

The Project Manager will be juggling multiple jobs during the construction phase keeping up with marketing efforts, problem-solving with the Architect and Engineers about construction site issues as they arise, making sure that construction draws are timely and accurate, and keeping the Board of Directors, the Housing and Development Committee and all other stakeholders and constituencies informed as to the progress for the project.

Marketing Follow-up on For-Sale Housing

The Project Manager may meet weekly with sales agents during construction of the project in order to stay informed about the status of marketing efforts. It will be important to follow up with agents on logs that detail calls, call-backs, walk-in traffic, first and second visits to the marketing office. If the policy is to offer interested buyers options to customize projects then the coordination between the GC and the build-out of those projects becomes even more critical to the construction schedule. Keeping the progress of construction going according to the schedule provided to the marketing agents is imperative so that buyer closings and construction closings remain on parallel paths.

If marketing is going slowly then decisions must be made on attracting buyers -- offering incentives which do not severely impact on sales margins, or increasing marketing coverage through creative and new promotions.

Services Programs for the Project/Taking Rental Applications

During the construction phase of the project, the Project Manager will prepare for the handoff of the building to the Property Management Company and the service providers. Space may be built-out for the service program in the new facility which must be inspected by the provider at the close of construction.

6. Board and Internal – Response/Reports

Coordination with Internal Departments:

Accounting

The Accounting Department of the Developer will request copies of all closing statements from the construction closing in order to book the debt and all revenues received on behalf of the project. This Accounting Department will receive copies of each draw – one set for their own records and one set for the auditor. The Project Manager will keep the Accounting Department informed regarding the cash flow from the Title Company as funds flow in and out of the project.

Property Management

The Project Manager will be working with the Property Management Department to

Coordinate the hand-off of the project to their staff at the completion of the project. Lease-up of the building will be monitored to ensure that it is on track and will not cause additional cost to the organization with vacancies occurring at the hand-off. Because the construction schedule will impact those who are planning to move into the building, close communication must be maintained between the General Contractor, the Project Manager, and the Property Management Department on the progress of construction.

Reporting to the Board/Housing Committee

The Project Manager will provide monthly updates to the Housing and Development Committee and they will in turn report to the Board on the progress of the development project. Only major problems and issues become part of their discussion agenda, otherwise reports are for “information only”. These progress reports should include items that directly impact the construction schedule, the marketing progress of lease-up or sales, and concerns of the stakeholders; the reports will become part of the minutes of the Board of Directors.

1. Organization of Key Project Information

The filing system for any project is the key to keeping the project organized. Complete records and their accessibility will keep the work on the project running smoothly.

SAMPLE: For-Sale Condo filing system* may be broken down into:

1. Acquisition (appraisal, deeds, closing docs, purchase agreement, title)

2. Construction (architect, const bidding, demo, draws, construction schedule)

3. Environmental (Phase I, lead and asbestos, geotechnical, hazardous materials)

4. Finance (predevelopment, pro forma, taxes, invoices, schedules)

5. Tax Credit – Limited Partners (engagement letter, carryover, guarantees)

6. Insurance (general liability, builder’s risk, architect, property)

7. Community/Government (zoning, site plan review, neighbourhood support)

8. Marketing/Management (study, PR, groundbreaking, demographics, sales)

9. Closing Files (resolutions, checklists)

10. Partnership Organization (organizational docs, mission/roles, agreements)

* This system for filing was developed around projects that have received concept and financing approval and have moved ahead to close on construction financing.